## RoughEstimations
SUMMARY:
Effort estimation (Backlog Size): | 114
Confidence Level: | 80%
Expected duration with 0,8 confidence (sprints): | 16
Sprint cost: | 10000
Budget estimation: | 160000
0 risks identified, 0 with high possible impact
Model Parameters
| Mean | Std. Deviation | Comment
Expected Velocity (FTE/week): | 15 | 5
Expected requirements flaw (FTE/week): | 5 | 10
Note on B2: This field is calculated as sum of story-point of backlog items (see Backlog Sheet)
Note on B3: This parameter can be adjusted. The model works poorely for very low (<20%) and high (> 80%) probabilities
Note on B6: This field is calculated based on desired confidence level
Note on B12: This parameter reflects expected team velocity (how many story points they could deliver in average)
Note on C12: This parameters reflects standard deviation of the team velocity (how stable their velocity is. Higher values means less stability)
Note on B13: This parameter shows how many additional story points in average customer would return to the backlog after the demo (requirements inflow)
Note on C13: This parameter reflects expected deviation from average requirements inflow

## Backlog
BACKLOG
Phase | Stage | Estimate (SP) | Comment
Inception | Create architecture concept | 8
Elaboration | Create prototype | 8
Construction | Implement User Story 1 | 2
| Implement User Story 2 | 4
| Implement User Story 3 | 8
| Implement User Story 4 | 16
| Implement User Story 5 | 2
| Implement User Story 6 | 4
| Implement User Story 7 | 8
| Implement User Story 8 | 16
| Implement User Story 9 | 2
| Implement User Story 10 | 4
Transition | Documentation development | 16
| Release | 16
TOTAL: |  | 114

## Risks
RISKS
Risk Description | Probability | Impact | Comment

## Calcs
| N | Cumulative | Probability
0 | 1 | 0 | 0 | 10 | 11.1803
0 | 2 | 1.3816e-09 | 1.3816e-09 | 20 | 15.8114
0 | 3 | 7.1977e-06 | 7.1963e-06 | 30 | 19.3649
0 | 4 | 0.00046751 | 0.00046032 | 40 | 22.3607
0 | 5 | 0.0052336 | 0.0047661 | 50 | 25
0 | 6 | 0.024316 | 0.019083 | 60 | 27.3861
0 | 7 | 0.068445 | 0.044129 | 70 | 29.5804
0 | 8 | 0.14115 | 0.072703 | 80 | 31.6228
0 | 9 | 0.23714 | 0.095989 | 90 | 33.541
0 | 10 | 0.34606 | 0.10892 | 100 | 35.3553
0 | 11 | 0.45705 | 0.11099 | 110 | 37.081
0 | 12 | 0.56156 | 0.10451 | 120 | 38.7298
0 | 13 | 0.65428 | 0.092726 | 130 | 40.3113
0 | 14 | 0.73287 | 0.078587 | 140 | 41.833
0 | 15 | 0.79712 | 0.064251 | 150 | 43.3013
1 | 16 | 0.84816 | 0.051042 | 160 | 44.7214
0 | 17 | 0.88778 | 0.039617 | 170 | 46.0977
0 | 18 | 0.91795 | 0.030167 | 180 | 47.4342
0 | 19 | 0.94056 | 0.022611 | 190 | 48.734
0 | 20 | 0.95728 | 0.016724 | 200 | 50
0 | 21 | 0.96952 | 0.012232 | 210 | 51.2348
0 | 22 | 0.97838 | 0.0088617 | 220 | 52.4404
0 | 23 | 0.98475 | 0.0063675 | 230 | 53.619
0 | 24 | 0.98929 | 0.004543 | 240 | 54.7723
0 | 25 | 0.99251 | 0.0032214 | 250 | 55.9017
0 | 26 | 0.99478 | 0.002272 | 260 | 57.0088
0 | 27 | 0.99638 | 0.0015948 | 270 | 58.0948
0 | 28 | 0.99749 | 0.0011149 | 280 | 59.1608
0 | 29 | 0.99827 | 0.00077645 | 290 | 60.208
0 | 30 | 0.99881 | 0.00053899 | 300 | 61.2372
0 | 31 | 0.99918 | 0.00037305 | 310 | 62.2495
0 | 32 | 0.99944 | 0.00025752 | 320 | 63.2456
0 | 33 | 0.99961 | 0.00017735 | 330 | 64.2262
0 | 34 | 0.99974 | 0.00012188 | 340 | 65.192
0 | 35 | 0.99982 | 8.3594e-05 | 350 | 66.1438
0 | 36 | 0.99988 | 5.7235e-05 | 360 | 67.082
0 | 37 | 0.99992 | 3.9125e-05 | 370 | 68.0074
0 | 38 | 0.99994 | 2.6707e-05 | 380 | 68.9202
0 | 39 | 0.99996 | 1.8206e-05 | 390 | 69.8212
0 | 40 | 0.99997 | 1.2396e-05 | 400 | 70.7107
0 | 41 | 0.99998 | 8.4302e-06 | 410 | 71.5891